## Time Sheet
Timesheets
Date | Func. Domain | Sprint | Phase | Budget code | Employee | Description | Hours
2026-01-02 | A00 | S1 | 100 | A00-S1-100 | Paul G. | Activity description .. | 8
2026-01-02 | A00 | S1 | 100 | A00-S1-100 | Paul G. | Activity description .. | 4
2026-01-04 | A00 | S1 | 200 | A00-S1-200 | Paul G. | Activity description .. | 8
2026-01-04 | B00 | S1 | 100 | B00-S1-100 | Jean V. | Activity description .. | 8
2026-01-04 | B00 | S1 | 200 | B00-S1-200 | Jean V. | Activity description .. | 8
2026-01-10 | B00 | S1 | 300 | B00-S1-300 | Chris F. | Activity description .. | 8

## Budget
Budget assignments
Date | Func. Domain | Sprint | Phase | Budget code | Description | Budget in Hours
2026-01-01 | A00 | S1 | 100 | A00-S1-100 | budget assignment for the analysis phase | 22
2026-01-01 | B00 | S1 | 100 | B00-S1-100 | budget assignment for the analysis phase | 32
2026-01-01 | A00 | S1 | 200 | A00-S1-200 | budget assignment for the prototype presentation phase phase | 22
2026-01-01 | A00 | S1 | 300 | A00-S1-300 | budget assignment for the Setup phase | 30
2026-01-13 | A00 | S1 | 100 | A00-S1-100 | budget reallocation to the following phase | -1
2026-01-13 | A00 | S1 | 200 | A00-S1-200 | budget reallocation to the following phase | 1

## Dashboard
Project Dashboard
|  |  |  | Sprint | S1 | SPRINT 1
|  |  |  | Phase | 100 | Analysis phase |  |  | 200 | Solution presentation |  |  | 300 | Setup |  |  | >>>
Functional Domain |  | Totals by domain |  |  | Budget code | Budget | Consummed | Remaining Hours | Budget code | Budget | Consummed | Remaining Hours | Budget code | Budget | Consummed | Remaining Hours
|  | Budget | Consummed | Remaining Hours
A00 | Gen. Accounting | 22 | 20 | 2 | A00-S1-100 | 21 | 12 | 9 | A00-S1-200 | 23 | 8 | 15 | A00-S1-300 | 30 | 0 | 30
B00 | Sales Accounting | 0 | 24 | -24 | B00-S1-100 | 32 | 0 | 32 | B00-S1-200 | 0 | 0 | 0 | B00-S1-300 | 0 | 0 | 0
| TOTALS | 22 | 44 | -22